## Sheet1
Date | Project | Work | Remarks | Status | Completion Date
2024-02-02 | Lead Management System | Listed the various LMS features | I visited and Analysed the following websites Solid perfo- rmers,Pipedrive links&videos | Completed | 2024-02-02
2024-05-02 | Lead Management System | SMS Services | Reviewed the API documentation for the 2factor service to understand how to utilize the API for both transactional and promotional SMS purposes. | Completed | 3/2/2024
2024-06-02 | Lead Management System | LMS layouts,table structures | Prepared a layout for lead management and prepared table structures. | Completed | 2024-06-02
2024-07-02 | Lead Management System | Table creation for LMS | Created tables and inserted values into the table. |  | 2024-07-02
2024-08-02 | Lead Management System | Login page creation | successfully created login page. | Completed | 2024-08-02
2024-09-02 | Lead Management System | Admin Login page creation | Due to SQL server connection issue, we have not completed the work. | Pending | 2024-09-02
2024-10-02 | Lead Management System | Admin Login page creation | Created admin login page, created role,hierarchy tables | Completed | 2024-10-02
2024-11-02 | Lead Management System | Manager Login page | Created manager login page and added drop down and a submit button. | Completed | 2024-11-02
2024-12-02 | Lead Management System | Manager Login page | Created tables for Manager, marketing executive and a drop down and button is provided for assigning the leads. | Pending
13/2/2024 | Lead Management System | Manager Login page | Created tables for Manager, marketing executive and a drop down and button is provided for assigning the leads. | Pending
14/2/2024 | Lead Management System | Table dta in grid format | Display table data in gridview | Completed | 14/02/2024
14/2/2025 | Lead Management System | Assign Button in Manager Page | It is not working properly | pending